## Slide 1
INCEPTION REPORT
Routine Data Quality Audits (RDQAs)
Tiko Africa – Uganda Programme
Kampala & Wakiso Districts | March – December 2026
Paul Mubiri • Lead Consultant / Team Leader
Raymond R. Wayesu • Data Analyst / Biostatistician
13 February 2026
Interactive Demo: rdqa-demo.vercel.app
RDQA Web Tool: dnfxdz-raymond-wayesu.shinyapps.io/rdqa-web-tool/

## Slide 2
AGENDA
Inception
Presentation
01
Assignment Overview & Understanding
02
Team Structure & Roles
03
RDQA Methodology & Frameworks
04
Dual-System Verification Approach
05
Monthly RDQA Process
06
Work Plan & Timeline
07
Digital Tools & Instruments
08
Risk Matrix & Mitigation
09
KCCA & Wakiso Engagement Strategy
10
Next Steps

## Slide 3
ASSIGNMENT OVERVIEW
54
Health
Facilities
10
Monthly
Cycles
3
Quarterly
Review Sessions
2
Districts
(Kampala & Wakiso)
The Core Challenge
Tiko’s digital data pipeline and Uganda’s paper-based HMIS reporting system operate in parallel. Discrepancies between these systems must be identified, root-caused, and resolved through collaborative corrective action. This RDQA will bridge Tiko’s innovative digital ecosystem with national reporting standards across Kampala and Wakiso Districts.
Service Areas:
SRH / Family Planning
HIV Testing & ART
SGBV Response
Mental Health
Demand Generation

## Slide 4
TEAM STRUCTURE & ROLES
LEAD CONSULTANT / TEAM LEADER
Paul Mubiri
MSc Biostatistics (Makerere) • 13+ years
RDQA experience: PTBi, MGIC, iTECH
Tools: DHIS2, KoboToolbox, STATA, R, REDCap
Publications: 20+ peer-reviewed papers (Lancet, BMC, PLOS)
Key skills: Data quality assessment, protocol development, M&E capacity building, PEPFAR/USAID systems
DATA ANALYST / BIOSTATISTICIAN
Raymond R. Wayesu
MSc Statistics (Linköping) • 10+ years
DQ experience: UVRI, Sanyu Africa, NSSF, iTECH
Tools: R, Python, SQL, Linux, GCP certified
Specialisms: Biostatistics, clinical trials, machine learning, data quality control
Key skills: Statistical modelling, digital instrument development, dashboards, verification factor computation
Core two-person team; additional field support to be mobilised if facility volume requires (Kampala/Wakiso-based, 3+ years HMIS experience)

## Slide 5
RDQA METHODOLOGY & FRAMEWORKS
MEASURE Evaluation
RDQA Tool
Part 1: Data Verification
• Recount from source documents
• Verification Factor (VF) computation
• ±10% tolerance band
Part 2: Systems Assessment
• 5 functional areas scored 1–3
• Spider chart visualisation
WHO Data Quality
Review Toolkit
Four quality dimensions:
• Completeness & timeliness
• Internal consistency
• External consistency
• Population data comparison
Desk review + field verification
Uganda MoH
HMIS Guidelines
National DQ attributes:
• Accuracy & validity
• Completeness & uniqueness
• Consistency & timeliness
Aligns with HMIS registers
(031, 055B, 071, 074, 080/081)

## Slide 6
DUAL-SYSTEM VERIFICATION APPROACH
Three-way data triangulation across Tiko Platform, facility source documents, and national DHIS2
Tiko Platform
Real-time digital records
SMS / WhatsApp / App
AI fraud detection & GPS
Facility HMIS
Registers
HMIS 031, 055B, 071, 074
080/081, tally sheets
HMIS 105 monthly summary
National DHIS2
District-level aggregates
District Biostatistician entry
WHO DQ App desk review
Verification Factor (VF)
VF = Recounted Value ÷ Reported Value × 100%
Acceptable range: 90% – 110% (±10% tolerance band)
< 90%
Over-reporting
90–110%
Acceptable
> 110%
Under-reporting

## Slide 7
MONTHLY RDQA PROCESS
PHASE 1
Pre-Visit Preparation
Days 1–3
Receive facility list & indicator priorities from Tiko
DHIS2 desk review using WHO DQ App
Coordinate with KCCA & Wakiso DHTs
Pre-load KoboToolbox instruments
Review previous month’s action points
PHASE 2
On-Site RDQA
Days 4–18
Deploy 2–3 person sub-teams per facility
Recount from primary HMIS registers
Compare against Tiko Platform & HMIS 105
Compute VFs; photograph register pages
Root cause interviews with facility staff
Verify closure of previous action points
PHASE 3
Analysis & Reporting
Days 19–25
Clean & validate KoboToolbox data
Compute final VFs & spider charts
Compile individual facility reports
Update action point tracker
Submit datasets & reports to Tiko by 25th

## Slide 8
WORK PLAN & TIMELINE
Activity | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Inception & Tool Dev |  |  |  |  |  |  |  |  |  | 
Monthly RDQA Cycles |  |  |  |  |  |  |  |  |  | 
Post-RDQA Follow-ups |  |  |  |  |  |  |  |  |  | 
Q1 Data Review |  |  |  |  |  |  |  |  |  | 
Q2 Data Review |  |  |  |  |  |  |  |  |  | 
Q3 Data Review + Final |  |  |  |  |  |  |  |  |  | 
Strategic Analysis |  |  |  |  |  |  |  |  |  | 
Monthly Deliverables
Final cleaned dataset (Excel/CSV)
Individual facility reports with VF tables
Action point tracker (Closed / Pending / Overdue)
Quarterly Deliverables
Facility Data Review Report (attendees, trends, commitments)
Strategic Insights Report (cross-division patterns, systemic gaps)

## Slide 9
DIGITAL TOOLS & INSTRUMENTS
KoboToolbox — Primary RDQA Platform
Offline capability: KoboCollect Android app works without internet
Skip logic & validation: Built-in rules prevent entry errors
Auto-calculated VFs: Real-time Verification Factor computation
GPS auto-capture: Automatic facility geolocation logging
Photo documentation: Forced-capture of register pages (no gallery)
Audit metadata: Form start/end times, enumerator tracking
RDQA Instrument
Structure
1
Facility ID
GPS, cascading selects, assessor info
2
Data Verification
Repeat group per indicator, auto VF calc
3
Systems Assessment
Likert scales, 5 functional areas
4
Action Plan
Issues, priority, responsible, timeline
Cost: Free humanitarian tier (5,000 submissions/month, 1 GB storage)
RDQA Demo Dashboard
Interactive demonstration of our analytical outputs — VF charts, spider diagrams, root cause analysis, and three-way data triangulation: https://rdqa-demo.vercel.app/
RDQA Web Tool (R/Shiny)
Live interactive application for real-time VF computation, M&E systems assessment, datimvalidation checks, and report generation — supports demo mode and live DHIS2 integration: https://dnfxdz-raymond-wayesu.shinyapps.io/rdqa-web-tool/

## Slide 10
RISK MATRIX & MITIGATION
Risk | Likelihood | Impact | Mitigation Strategy
Facility staff reluctant to participate in RDQA process | Medium | High | Pre-visit coordination with facility in-charges via Tiko; frame RDQA as supportive (not punitive); provide verbal feedback on-site
Stock-out of HMIS registers at facilities | High | Medium | Use any available primary source documents; document gaps; triangulate with Tiko Platform and DHIS2 data
Poor internet connectivity during field visits | Medium | Low | KoboCollect offline mode; all forms pre-loaded before deployment; sync upon return to coverage area
Delays in Tiko providing facility lists or data exports | Medium | Medium | Agree data-sharing SLA during inception; build 3-day buffer into monthly timeline; maintain rolling facility schedule
High field auditor turnover during 10-month engagement | Low | High | Competitive daily rates; clear onboarding protocol; cross-train all auditors on all modules; maintain backup auditor pool
Discrepancies caused by genuine indicator definition misunderstandings | High | Medium | Include indicator definition reference sheets in RDQA instruments; harmonise definitions with Tiko during inception

## Slide 11
KCCA & WAKISO ENGAGEMENT STRATEGY
KAMPALA (KCCA)
8 KCCA-managed + private sector
Key contact: KCCA Health Department
Introduction meeting with KCCA Health Director
Invite KCCA Health Information Officers to joint facility visits
Share summary findings (with Tiko consent)
Align RDQA schedule with KCCA supervision calendar
WAKISO DISTRICT
72 government + 477 private facilities
Key contact: District Health Officer & Biostatistician
Courtesy call to Wakiso DHO at district headquarters
Request District Biostatistician to co-verify DHIS2 entries
Coordinate with sub-county health teams for facility access
Feed findings into District Health Management Team reviews
Monthly coordination calls with Tiko programme team to align facility schedules, share preliminary findings, and adjust audit plans

## Slide 12
NEXT STEPS
1
Week 1
Finalise inception details
Sign contract; confirm facility list with Tiko; finalise indicator selection; recruit field auditors
2
Week 2
Tool development & training
Build & test custom KoboToolbox RDQA instrument; 2-day field auditor training; pilot at 2–3 facilities
3
Week 3
Stakeholder introductions
Courtesy meetings with KCCA Health Department and Wakiso District Health Officer; present RDQA scope
4
Week 4
First RDQA cycle launch
Deploy field teams for March RDQA; begin on-site data verification across priority facilities
Paul Mubiri: mubirip@gmail.com | +256 754 544 660 • Raymond Wayesu: raymondrwayesu@gmail.com | +256 784 902 753
Interactive RDQA Demo: https://rdqa-demo.vercel.app/
RDQA Web Tool (R/Shiny): https://dnfxdz-raymond-wayesu.shinyapps.io/rdqa-web-tool/